## Feature Backlog
ID | Phase | Feature Area | Feature | User Story | Acceptance Criteria | Priority | Effort (Days) | Dependencies | Revenue Impact | Status
GC-001 | P0 — MVP (Oct 2026) | Infrastructure | Project scaffolding | As a developer, I want a Next.js 14 project with Supabase, Tailwind, and shadcn/ui configured so I can start building features | Next.js App Router, TypeScript, Tailwind, shadcn/ui, Supabase client, Vercel deployment pipeline, environment variables configured | Critical | 2 | None | None | To Do
GC-002 | P0 — MVP (Oct 2026) | Infrastructure | Design token system | As a developer, I want a CSS custom property system for colours, spacing, typography, and shadows so every component uses consistent tokens | All tokens from the brief implemented as CSS variables. Semantic colour tokens. 8px spacing rhythm. Fraunces + DM Sans loaded via next/font. Dark mode tokens defined but not active in v1 | Critical | 1 | GC-001 | None | To Do
GC-003 | P0 — MVP (Oct 2026) | Infrastructure | Supabase schema and RLS | As a developer, I want all database tables, relationships, and Row Level Security policies created so the app has a secure data layer | All 8 tables (User, Group, GroupMember, Exclusion, Draw, WishlistItem, AnonMessage, BabyPhoto) created with RLS policies. Anonymous auth enabled. Storage bucket for photos with group-scoped access | Critical | 2 | GC-001 | None | To Do
GC-004 | P0 — MVP (Oct 2026) | Infrastructure | Anonymous auth flow | As a user, I want to create or join a group without creating an account so there is zero friction | Supabase anonymous auth on group creation and join. Session cookie persists across tabs. Optional email upgrade shown post-draw. Magic link login for returning users. No forced registration anywhere | Critical | 2 | GC-003 | None | To Do
GC-005 | P0 — MVP (Oct 2026) | Landing Page | Homepage hero and features | As a visitor, I want to understand what GiftCircle does and create a draw within 10 seconds so I don't bounce | Hero with headline, subheadline, and CTA from the brief. 6 feature blocks. Trust line below CTA. Subtle festive CSS animation (snowfall or twinkle). Mobile-first responsive. Page load under 2s. No generic AI aesthetics — distinctive typography and warm colour palette | Critical | 3 | GC-002 | High | To Do
GC-006 | P0 — MVP (Oct 2026) | Landing Page | SEO metadata and OG tags | As a marketer, I want proper page titles, descriptions, and Open Graph images so the site ranks and shares well | Title: 'GiftCircle — Free Secret Santa Generator with Wishlists and Gift Ideas'. OG image designed for WhatsApp/social preview. Structured data (Organization, WebApplication). Sitemap generated | High | 1 | GC-005 | High | To Do
GC-007 | P0 — MVP (Oct 2026) | Group Creation | Create group wizard | As an organiser, I want to create a Secret Santa group in under 60 seconds so it feels effortless | Single-page wizard: group name, mode selector (4 cards), budget pills (£5–£25 + custom), exchange date (optional), location (optional), organiser name. CTA: 'Create your draw'. All fields have visible labels. Mobile single-column layout. Sticky CTA button. Progressive disclosure for optional fields | Critical | 3 | GC-004 | None | To Do
GC-008 | P0 — MVP (Oct 2026) | Group Creation | Invite link and share screen | As an organiser, I want to share my group via WhatsApp, copy link, or QR code so everyone can join instantly | Unique invite code generated (URL-safe, short). Share screen with: copy link button, WhatsApp share (pre-filled message), QR code. Live member counter updates as people join. Link format: giftcircle.app/join/[code] | Critical | 2 | GC-007 | None | To Do
GC-009 | P0 — MVP (Oct 2026) | Join Flow | Join via invite link | As a participant, I want to join a group by tapping a WhatsApp link and entering my name so I don't need to download anything | Join page shows: group name, mode, budget, date, member count, organiser name. Single form field: 'Your name'. CTA: 'Join this Secret Santa'. No account required. After joining: prompted (not forced) to add likes/dislikes and wishlist items. Mobile-optimised with appropriate keyboard type | Critical | 2 | GC-008 | None | To Do
GC-010 | P0 — MVP (Oct 2026) | Dashboard | Group dashboard with tab navigation | As a group member, I want a clean tabbed interface so I can navigate between Draw, Wishlists, Messages, and Games | Bottom tab bar on mobile (4 tabs max). Lucide icons, no emoji. Top bar: group name, member count, settings gear. Tab transitions are smooth. Notification badges on Messages (unread dot) and Wishlists (new items). Safe area compliance for notch and gesture bar | Critical | 3 | GC-009 | None | To Do
GC-011 | P0 — MVP (Oct 2026) | Dashboard | Organiser status dashboard | As an organiser, I want to see who has joined, who has added wishlists, and whether the draw is ready so I can manage the group | Progress checklist with completion percentage. Member list with status indicators (joined ✓, wishlist ✓). Exclusion rules editor. 'Draw Names' button (disabled until 3+ members). Redraw warning modal | High | 2 | GC-010 | None | To Do
GC-012 | P0 — MVP (Oct 2026) | Draw System | Draw algorithm with exclusions | As an organiser, I want names drawn fairly with exclusion rules so couples and siblings don't draw each other | Derangement algorithm: nobody gets themselves, all exclusions respected, every person gives and receives exactly one gift. If no valid draw possible, clear error message explaining why. Draw results stored per-user. Organiser cannot see individual matches. Draw locks after completion — redraw requires confirmation | Critical | 3 | GC-011 | None | To Do
GC-013 | P0 — MVP (Oct 2026) | Draw System | Name reveal animation | As a participant, I want an exciting reveal of who I'm buying for so the moment feels special and shareable | Screen 1: 'Ready to find out?' + reveal button. Screen 2: 2–3 second cinematic animation (envelope open or card flip). Screen 3: 'You're buying for... [Name]' with recipient's likes, wishlist, budget, and action buttons. Respects prefers-reduced-motion. Must look polished enough to screenshot and share on WhatsApp | Critical | 4 | GC-012 | None | To Do
GC-014 | P0 — MVP (Oct 2026) | Draw System | Trust messaging | As a participant, I want to see that the draw is fair and private so I trust the result | Post-draw confirmation: 'All X people matched successfully ✓'. Privacy message: 'Your match is private. Nobody else can see who you picked.' Lock icon: 'Draw is locked.' Organiser restriction: 'The organiser cannot see individual matches.' | High | 1 | GC-013 | None | To Do
GC-015 | P0 — MVP (Oct 2026) | Wishlists | Add and edit wishlist items | As a participant, I want to add gift ideas from any shop so my Secret Santa knows what I want | Add form: title (required), link (any URL), price (£), notes, priority (Would love / Would like / Just inspiration). Sections: 'Things I'd love', 'Things like this', 'Please avoid', 'My sizes'. Retailer-neutral — no Amazon bias. Edit and delete items. Empty state drives action with preview and CTA | Critical | 3 | GC-010 | High | To Do
GC-016 | P0 — MVP (Oct 2026) | Wishlists | View others' wishlists and mark as bought | As a buyer, I want to see my recipient's wishlist and mark items as bought so gifts aren't duplicated | Read-only view of each member's wishlist. 'I'm getting this' toggle — hidden from recipient, visible to other buyers. Links open in new tab. Shop name auto-detected from URL if possible | High | 2 | GC-015 | Medium | To Do
GC-017 | P0 — MVP (Oct 2026) | Messaging | Anonymous messaging system | As a buyer, I want to ask my recipient questions without revealing my identity so I can buy a better gift | Buyer sends as 'Your Secret Santa 🤫'. Recipient sees message but not sender. Reply goes back to buyer privately. Chat bubble UI. Suggested question chips (6 pre-written prompts). 500 char limit. 10 messages/day rate limit. Report button on each message. No images or links in messages | Critical | 4 | GC-012 | None | To Do
GC-018 | P0 — MVP (Oct 2026) | Gift Ideas | Curated gift guide pages | As a user, I want to browse gift ideas filtered by budget so I can find something good quickly | Static/SSG pages for: under £5, £10, £15, £20, £25, colleague, funny, cosy. Each gift card: image (WebP, lazy loaded), name, price, shop, affiliate link (rel='noopener sponsored'), tags. Affiliate disclosure footer. In-app link from reveal screen: 'Find gifts under £[budget]' | High | 4 | GC-002 | Critical | To Do
GC-019 | P0 — MVP (Oct 2026) | Games | Guess the Baby game | As a group member, I want to play Guess the Baby so we have fun beyond just drawing names | Upload phase: each member uploads a baby photo with consent message. Game phase: photos shuffled, guess who each photo belongs to. Results: leaderboard, reveal screen, fun stats. Privacy: Supabase Storage private bucket, group-scoped RLS, delete button always available, auto-delete after 30 days. Minimum 4 photos to start | High | 5 | GC-010 | Medium | To Do
GC-020 | P0 — MVP (Oct 2026) | Infrastructure | Mobile responsiveness QA | As a user, I want the app to work perfectly on my phone so I can use it from WhatsApp | Tested on: iPhone Safari, iPhone Chrome, Android Chrome, Android Samsung Browser. Touch targets ≥ 44×44px. No horizontal scroll. Bottom nav clears gesture bar. Forms use appropriate keyboard types. Sticky CTAs. Single-column layouts on mobile | Critical | 3 | All P0 features | None | To Do
GC-021 | P1 — Launch Polish (Nov 2026) | Notifications | Email — draw results | As a participant who provided their email, I want to be notified when names are drawn so I don't miss the reveal | Transactional email via Resend. Subject: 'Names have been drawn! 🎅 Open GiftCircle to see your match.' Links back to reveal screen. Only sent to users who provided an email. Unsubscribe option | High | 2 | GC-013 | None | To Do
GC-022 | P1 — Launch Polish (Nov 2026) | Notifications | Email — new anonymous message | As a recipient, I want to be notified when my Secret Santa asks me a question so I can reply | Email: 'Your Secret Santa has a question for you 🤫'. Links to messages tab. Batched — max 1 email per hour to avoid spam | Medium | 1 | GC-017 | None | To Do
GC-023 | P1 — Launch Polish (Nov 2026) | Notifications | Organiser reminder nudges | As an organiser, I want to remind people who haven't joined or added wishlists so the group is complete before the draw | Organiser dashboard shows who hasn't joined and who hasn't added wishlist items. 'Send reminder' button re-shares the invite link. 'Nudge to add wishlist' sends a group-level prompt | Medium | 2 | GC-011 | None | To Do
GC-024 | P1 — Launch Polish (Nov 2026) | Gift Ideas | Gift ideas for foodies and eco categories | As a user browsing gifts, I want more category options so I can find the right type of gift | Add pages: /gifts/foodies, /gifts/eco. Curated products with affiliate links. Same card format as existing pages | Medium | 2 | GC-018 | High | To Do
GC-025 | P1 — Launch Polish (Nov 2026) | Landing Page | Social proof counter | As a visitor, I want to see how many groups have been created so I trust the product | Live counter: 'X groups created this week' or 'X names drawn'. Updates from Supabase aggregate query. Positioned near the CTA. Formatted with commas for large numbers | Medium | 1 | GC-005 | Medium | To Do
GC-026 | P1 — Launch Polish (Nov 2026) | Landing Page | Testimonial section | As a visitor, I want to see real user feedback so I feel confident creating a group | 3–5 testimonial cards with name, role/context (e.g. 'Office organiser'), and quote. Carousel on mobile. Static grid on desktop. Added after beta feedback is collected | Low | 1 | GC-005 | Medium | To Do
GC-027 | P1 — Launch Polish (Nov 2026) | Accessibility | Full WCAG 2.1 AA audit | As a user with accessibility needs, I want the app to meet WCAG 2.1 AA standards so I can use it fully | 4.5:1 contrast on all text. Focus rings on all interactive elements. Screen reader tested (VoiceOver, TalkBack). Skip links. Sequential heading hierarchy. prefers-reduced-motion honoured. All icon buttons have aria-labels. Form fields have visible labels. Colour never the only indicator | High | 3 | All P0 features | None | To Do
GC-028 | P1 — Launch Polish (Nov 2026) | Performance | Core Web Vitals optimisation | As a user on a slow connection, I want the app to load fast so I don't abandon the page | LCP < 2.5s. FID < 100ms. CLS < 0.1. Images optimised (WebP, lazy loaded, reserved space). Fonts preloaded. Code-split per route. Lighthouse score > 90 on all pages | High | 2 | All P0 features | None | To Do
GC-029 | P1 — Launch Polish (Nov 2026) | SEO | Gift guide SEO optimisation | As a marketer, I want gift guide pages ranking on Google before November so we capture seasonal search traffic | Keyword-optimised titles and meta descriptions. Internal linking between gift pages. Breadcrumbs. Schema markup (Product, ItemList). Alt text on all images. Target keywords: 'secret santa gifts under £10 UK', 'office secret santa ideas', 'funny secret santa gifts' | High | 2 | GC-018 | Critical | To Do
GC-030 | P1 — Launch Polish (Nov 2026) | Analytics | Event tracking setup | As a product owner, I want to track key user actions so I can measure activation and conversion | Track: group created, invite link shared (by channel), member joined, wishlist item added, draw triggered, reveal viewed, anonymous message sent, gift link clicked (affiliate), game started, game completed. Plausible or PostHog — no cookies, privacy-first | High | 2 | All P0 features | Medium | To Do
GC-031 | P2 — Post-Launch (Jan 2027) | Games | Christmas Awards voting | As a group member, I want to vote on fun awards so we have more group entertainment | Pre-set award categories (Best Christmas Jumper, Most Likely to Finish the Snacks, etc.). Anonymous voting. Results revealed with animations. Shareable results card | Medium | 3 | GC-019 | Low | To Do
GC-032 | P2 — Post-Launch (Jan 2027) | Games | Guess the Wishlist game | As a group member, I want to guess who added which wishlist item so we can learn about each other | Show a wishlist item, players guess who added it. Score tracking. Results at end. Requires minimum wishlist items across group | Low | 2 | GC-015, GC-019 | Low | To Do
GC-033 | P2 — Post-Launch (Jan 2027) | Games | Christmas Trivia quiz | As a group member, I want to play a quick festive trivia game for fun | Pre-loaded question bank: films, songs, UK traditions. Timed rounds. Leaderboard. Organiser can add custom questions | Low | 3 | GC-019 | Low | To Do
GC-034 | P2 — Post-Launch (Jan 2027) | Games | This or That polls | As a group member, I want quick group polls to spark conversation | Fast binary polls: 'Mince pies or chocolate log?', 'Real tree or fake tree?'. Results shown live. Custom poll creation | Low | 2 | GC-019 | Low | To Do
GC-035 | P2 — Post-Launch (Jan 2027) | Draw System | Avoid last year's matches | As a returning organiser, I want to prevent repeat matches from last year so everyone gets someone new | If group was used last year, import previous draw as exclusion rules. Toggle: 'Avoid last year's matches'. Requires saved groups (email auth) | Medium | 2 | GC-012 | Low | To Do
GC-036 | P2 — Post-Launch (Jan 2027) | Groups | Saved yearly groups | As a returning user, I want my group saved so I can reuse it next Christmas | Email-authenticated users can access saved groups. 'Use this group again next year' prompt after Christmas. Pre-populated member list. Budget and rules carried over. Wishlist carried over | Medium | 3 | GC-004 | Medium | To Do
GC-037 | P2 — Post-Launch (Jan 2027) | Notifications | Scheduled gift buying reminders | As a participant, I want reminders to buy my gift before the exchange date so I don't forget | Email reminders at: 2 weeks before, 1 week before, 2 days before exchange date. Only sent to users who haven't marked their gift as bought. Opt-out link | Medium | 2 | GC-013, GC-021 | None | To Do
GC-038 | P2 — Post-Launch (Jan 2027) | Gift Ideas | Dynamic affiliate product feed | As a user, I want real-time gift suggestions from UK retailers so I see current stock and prices | Integrate Awin product feed API. Filter by price, category, retailer. Auto-tag products from wishlisted retailer URLs. Replace or supplement curated pages | Medium | 5 | GC-018 | Critical | To Do
GC-039 | P2 — Post-Launch (Jan 2027) | Infrastructure | Dark mode | As a user who prefers dark mode, I want the app to support my system preference | Dark mode using existing token system. Auto-detect from prefers-color-scheme. Manual toggle in settings. All surfaces, text, borders, and states tested in dark mode | Low | 3 | GC-002 | None | To Do
GC-040 | P2 — Post-Launch (Jan 2027) | Retention | Post-Christmas email sequence | As a product owner, I want to re-engage users in January so they return next Christmas | Email 1 (Boxing Day): 'How did it go? Rate your Secret Santa experience'. Email 2 (Jan): 'Your group is saved — see you next year'. Email 3 (Oct): 'It's time! Your [Group Name] is ready to go again' | Medium | 2 | GC-021 | Medium | To Do
GC-041 | P3 — Year-Round (2027+) | Multi-Occasion | Birthday gift exchange mode | As a family organiser, I want to use GiftCircle for birthday wishlists so the app is useful year-round | New group mode: Birthday. No draw needed — just wishlists and gift coordination. 'Mark as bought' to prevent duplicates. Date-based reminders | Medium | 4 | GC-036 | Medium | To Do
GC-042 | P3 — Year-Round (2027+) | Multi-Occasion | Eid gift exchange mode | As a Muslim family, I want to use GiftCircle for Eid gifting so I have a culturally relevant option | New group mode: Eid. Appropriate theming and language. Halal-friendly gift filter in gift ideas. Same core features as Christmas mode | Medium | 3 | GC-041 | Medium | To Do
GC-043 | P3 — Year-Round (2027+) | Multi-Occasion | Wedding and baby shower registries | As someone planning a life event, I want to share a wishlist with guests so I get gifts I actually want | New group mode: Registry. Public wishlist link (no draw). Mark as bought. Multiple price ranges. Notes for guests | Low | 4 | GC-041 | Medium | To Do
GC-044 | P3 — Year-Round (2027+) | Premium | Premium group features | As a power organiser, I want advanced features for large or complex groups so I can manage them better | Premium tier: larger groups (20+), avoid last year's matches, advanced exclusions, export results, multiple exchanges per group. Pricing: £2.99–£4.99 per group or £9.99/year. Core draw always free | Medium | 5 | GC-036 | High | To Do
GC-045 | P3 — Year-Round (2027+) | Premium | Workplace plan with branding | As an HR manager, I want to run Secret Santa for the whole company with our branding | Custom logo and colours. Admin dashboard. Department-level groups. Slack/Teams integration. Annual licence pricing. Employee count-based tiers | Low | 8 | GC-044 | High | To Do
GC-046 | P3 — Year-Round (2027+) | Mobile | iOS app (PWA or native) | As a mobile user, I want an app on my home screen with push notifications so I don't miss anything | Option A: PWA with service worker and push notifications. Option B: React Native wrapper. Push notifications for: draw results, new messages, reminders. App Store listing | Low | 10 | All P2 features | Medium | To Do
GC-047 | P3 — Year-Round (2027+) | Mobile | Android app (PWA or native) | As an Android user, I want an app with push notifications | Same as iOS. Play Store listing. Android-specific testing | Low | 8 | GC-046 | Medium | To Do
GC-048 | P3 — Year-Round (2027+) | Integrations | Slack integration | As a workplace organiser, I want to run Secret Santa inside Slack so the team doesn't need a separate app | Slack bot: create group, join, receive draw results, send anonymous messages. Slash commands. App directory listing | Low | 6 | GC-045 | Medium | To Do

## Summary
Phase | Features | Total Effort (Days) | Key Deadline
P0 — MVP | 20 | 52 | 1 Oct 2026
P1 — Launch Polish | 10 | 18 | 1 Nov 2026
P2 — Post-Launch | 10 | 27 | Jan 2027
P3 — Year-Round | 8 | 48 | 2027+
TOTAL | 48 | 145

## By Feature Area
Feature Area | Total Effort (Days)
Infrastructure | 13
Landing Page | 6
Group Creation | 5
Join Flow | 2
Dashboard | 5
Draw System | 10
Wishlists | 5
Messaging | 4
Gift Ideas | 11
Games | 15
Notifications | 7
Accessibility | 3
Performance | 2
SEO | 2
Analytics | 2
Retention | 2
Multi-Occasion | 11
Premium | 13
Mobile | 18
Integrations | 6